## Gantt Chart
| Sprint number and objective | Subtasks | Week 1 |  | Week 2 |  | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7 |  | Week 8 |  | Week 9 |  | Week 10 |  | Week 11 |  | Week 12 |  | Week 13 |  | Week 14 |  | Week 15 |  | Week 16 |  | Week 17 |  | Week 18 |  | Week 19 |  | Week 20 |  | Week 21 |  | Week 22 |  | Week 23 |  | Week 24
|  |  | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend | Weekday | Weekend
| 1: Set up basic mechanics | Plan Sprint and Design
Set up game program environment
Weekday = 5 hours |  | Draw and place basic objects
Weekend = 4 hours |  | Add Control
Add Collision
Add Physics
Test Prototype and Review
| 2: Score, health, pick-up items, obstacles | Plan Sprint and Design
Score, Health and HUD
Entity Superclass
Subclasses
Create Instances
Game over screen
Adjust platform layout
Adjust player speeds
Test and Review Prototype
| 3: Level/course mechanics | Plan Sprint
Design
Game adjustments
Add suggested features
Course mechanics
Levels
Testing
Review
| 4: Enemies | Plan Sprint
Design
Enemies
Combat
Testing
Review
| 5:Menu and other UI | Plan sprint and Design
Design GUI objects
Design Menus
GUI objects
Menu class
Main menu
Settings Menu
Testing
Review
| 6:Final additions | Plan Sprint
Design
Score by distance
Menu Navigation
Upgrade Shop
Settings
Testing
Review
| Evaluation | Testing for usability
Compare with success criteria
Show/explain features
Maintainability
Further Development

## Testing data
Feature | Test question | Test type | Test ref | Cases | Expected Output | Actual Output | Bugs | Success/Fixed?
Game environment | Will the window appear when executing the program? | Verify | 1.1.1 | Execute the program | A black window should appear | A black window appears | Nothing to close the window with, apart from terminating the program | Success
Draw basic shapes | White background? | Verify | 1.2.1 | Execute the program | Background of the window is white, a black rectangle at the bottom, 2 floating black platforms and a red square over the bottom rectangle | White background | The shapes seem to be very small, apart from the ground | Success
| Black rectangle at the bottom of the screen? | Verify | 1.2.2 |  |  | Black rectangle at bottom
| 2 black platforms floating | Verify | 1.2.3 |  |  | 2 Floating platforms
| Red square on top of ground? | Verify | 1.2.4 |  |  | Red square
Add control | Can the player move left to right? | Verify | 1.3.1 | Press the D key | The player should move right | The player doesn't move |  | Fixed
|  |  | 1.3.2 | Press the A key | The player should move left | The player moves left | The player goes very fast | Success
| Can the player jump? | Verify | 1.3.3 | Press the space key | The player should move up | The player moves up | The player can move up, but it can't get down | Success
| Can the player jump diagonally? | Verify | 1.3.4 | Press the A and the space key simultaneously | The player should move left-up | The player moves left-up |  | Success
|  |  | 1.3.5 | Press the D and the space key simultaneously | The player should move right-up | The player moves right-up |  | Success
| Can the program close? | Verify | 1.3.6 | Click the close button on the top right of the window | The program should close | The program closes |  | Success
| Will the game correctly respond to currently set controls? | Experimental | 1.3.7 | Assign the left key to the left arrow key, execute the program and press the left arrow key | The player should still move to the left | The player moves to the left |  | Success
|  |  | 1.3.8 | Assign the right key to the right arrow key, execute the program and press the right arrow key | The player should still move to the right | The player moves to the right |  | Success
|  |  | 1.3.9 | Assign the jump key to the up arrow key, execute the program and press the up arrow key | The player should still move up | The player moves up |  | Success
Add collision | Can the shapes still be drawn onto the window? | Verify | 1.4.1 | Launch the game | The shapes drawn before should still be shown | A white background, a large black rectangle, 2 small black rectangle and a red square is seen |  | Success
| Will the new movement variables still allow the player to move? | Verify | 1.4.2 | Launch the game and press the controls | The player should move | The player moves |  | Success
| Will the player be pushed back when moving into a platform? | Verify | 1.4.3 | Move the player under a platform and move up into the plaform | The player should stop at the bottom of the platform | The player stops moving once hitting the bottom of the platform |  | Success
|  |  | 1.4.4 | Align with a platform to the left and move to the right into the platform | Player should stop at the left side of the platform | The player stops at the left side |  | Success
|  |  | 1.4.5 | Align with a platform to the right and move to the left into the platform | Player should stop at the right side of the platform | The player stops at the right side |  | Success
| Will the player be pushed back when moving into a platform diagonally? | Experimental | 1.4.6 | Move into a platform diagonally | The player should stop moving on contact | The player stops moving on contact with the platform |  | Success
| Will collision apply to other platforms? | Verify | 1.4.7 | Move into the bottom of the second platform | Player should stop moving on contact | The player stops moving on contact with the bottom |  | Success
| When no keys are pressed, does the player stop? | Verify | 1.4.8 | Press either the A or D keys and then let go | The player should stop moving | The player keeps moving | The player does not stop moving | Fixed
|  |  | 1.4.9 | Press the space key and then let go | The player should stop moving | The player stops moving | The player stays mid-air and cannot come back down | Success
Add physics | Does the player gradually accelerate? | Verify | 1.5.1 | Press the D key | The player should accelerate to the right | The player does not move | The player can only move if its velocity is an integer value | Fixed
|  |  | 1.5.2 | Press the A key and see if the player speeds up to the left | The player should accelerate to the left | The player picks up speed as it moves to the left | The player can only move if its velocity is an integer value | Success
| Can the player change directions instantly? | Verify | 1.5.3 | Press the A key, and then press the D key | The player should move to the left, the immediately move to the right | The player moves left, then moves right |  | Success
|  |  | 1.5.4 | Press the D key and then press the A key | The player should move to the right, the immediately move to the left | The player moves right, then moves left |  | Success
| Is the player's speed restricted to the specified min_dx and max_dx values? | Verify | 1.5.5 | Get the program to print out player_dx onto the console. Track the value of player_dx | The speed value should not exceed the min_dx value | The speed value exceeds min_dx by 1 | The velocity does not stop at exactly the value of min_dx | Fixed
|  |  | 1.5.6 | Track the value of player_dx | The speed value should not exceed the max_dx value | The speed value exceeds max_dx by 1 | The velocity does not stop at exactly the value of min_dx | Fixed
| Will the player fall back to the ground while jumping? | Verify | 1.5.7 | Press space | The player should fall back to the ground | When min_dy is more than -1, the player does not move | When holding space, the player constantly jumps. Also, the player only moves at integer velocities | Fixed
| Is the player's falling speed restricted to the specified max_dy value? | Verify | 1.5.8 | Get the program to print player_dy on the console. Then fall off a high height from a platform | The player_dy value should not exceed max_dy | The player stays mid-air and only falls when pressimg space. Also, player_dy exceeds max_dy by 1 | When moving off a platform, the player does not fall. Also, velocity does not stop exactly at max_dy | Fixed
| Can the player stay on the ground once impacting the ground? | Verify | 1.5.9 | Jump and land on the ground | The player should stop moving on contact with the ground | The player hits the ground and stops moving |  | Success
| When jumping under a platform, will the player collide and fall back down? | Verify | 1.5.10 | Jump under a platform | The player should stop moving and fall down | The player stops and falls down. | The player stops, leaving a gap between the player and the platform | Success
| When colliding into a platform on the side, will the player be pushed off to the correct side and still fall back down? | Experimental | 1.5.11 | Jump into the side of a platform | The player should stop moving horizontally | The player stops moving horizontally, but also vertically | When jumping up on the side of the platform, the player stops and falls. | Success
HUD | Are all the hearts shown properly? | Verify | 2.1.1 | Launch the game and look under the hearts in the HUD | There should be 3 red squares in a row alligned with the hearts label | Only 2 hearts are shown as if the first heart is missing | The first heart is not shown. Also, there is no indication for max number of hearts | Fixed
| Are the text objects shown properly? | Verify | 2.1.2 | Launch the game and look at the text in the HUD | The text should be shown at about the size specified by the HUD design | The text is too smaller | Text font in the HUD is too small | Fixed
| Do the score and money variables work? | Verify | 2.1.3 | Have the score increment by 1 and money increment by 2 per tick. Launch the game and look at the Gold and Score values in the HUD | The Gold and Score values should show different values | The Gold value shows 202 and the Score value shows 101 |  | Success
Player | Will player functions still work? | Verify | 2.2.1 | Have the player collide into a platform | The player should stop moving on contact with the platform | The game crashes with attribute error | Private variable aren't inherited to subclasses. Player glitches when colliding into platform. | Fixed
|  |  | 2.2.2 | Press the player movement keys | The player should move | The player moves | When pressing the left and right keys simultaneously, the player slowly moves. Player only moves in integer velocities. | Success
Items | Do item effects work? | Verify | 2.3.1 | Collide into the Coin item | The gold value should increase by 1 | The game crashes with variable not found | Method apply_effect can't access global variable money | Fixed
|  |  | 2.3.2 | Collide into the Bandage item | The hearts should increase by 1 | One heart is added in the set of hearts |  | Success
|  |  | 2.3.3 | Collide into the Rum item | The player's health should increase to 3 and the player's horizontal velocity should decrease | The player's health fully heals to 3, but player's dx value doesn't change | Player's dx speed doesn't immediately change, only when changing directions | Fixed
| Are active effects managed properly? | Experimental | 2.3.4 | Have the console print out the player's active effects attribute. Pick up an item | The item's effect should be added into the effects list | After picking up a Rum item, its speed effect is added to the list | Effect only effective in the next tick (Low priority) | Success
|  |  | 2.3.5 | Wait for the effect duration after picking up an item | The effect list should be empty | The effect list is empty | Removal of effect only effective in the next tick (Low priority) | Success
|  |  | 2.3.6 | Gain two speed effects simultaneously | The two effects should be added to the list and then removed after their set durations | The two effects are added, but crashes when removing one effect with a list out of range error | For loop in update_effects method accesses index which is out of the list range | Fixed
|  |  | 2.3.7 | Gain one speed and one knockout effect | Effects should both be added, and shortly removed from the list | Both effects are added and then shortly removed |  | Success
Obstacles | Will the player be unable to move when colliding into an obstacle? | Verify | 2.4.1 | Collide into an obstacle. Then try moving by pressing left, right and jump key. | The player should not move after hitting an obstacle | The player can't move to the right and can't jump, but it can still move to the left | The player can move to the left after hitting an obstacle. When a negative score is shown, the font is missing a character for the negative sign | Fixed
| Will the player take damage when colliding into an obstacle? |  | 2.4.2 | Collide into an obstacle | The player's health should decrease by half a heart | The player's health reduces by half a heart |  | Success
Game over | Can the game over procedure trigger once player health reaches zero? | Verify | 2.5.1 | Set the player max health to 2 and hit both obstacles. | A black screen and the text "Game Over" should show up | Game crash with variable not found | HUD update procedure can't find list of hearts when health is 0 | Fixed
Hearts | Are the new hearts shown properly | Verify | 3.1.1 | Run the game and look at the HUD | The HUD should show one and a half hearts | Only one half heart is shown | Not all the hearts are drawn | Fixed
| Can health lost be shown? | Verify | 3.1.2 | Collide into an obstacle | Half a heart should be lost in the HUD | Half a heart is lost |  | Success
| Can health gained be shown? | Verify | 3.1.3 | Collide into an obstacle and then collide into a bandage/medkit | Half a heart should be gained in the HUD | The health increases by half a heart |  | Success
| Can different max health values change the max health shown on HUD? | Verify | 3.1.4 | Change the player's health to 10 | 5 whole hearts should show on the HUD | The HUD shows 5 hearts |  | Success
Jump | Can the player jump? | Verify | 3.2.1 | Press the up key | The player should still be able to jump | The player jumps |  | Success
| Does the jump height vary with different key hold durations? | Verify | 3.2.2 | Tap the up key | The player should jump at a short height | The player jumps, but at quite a high height | The player jumps too high | Fixed
|  |  | 3.2.3 | Hold the up key | The player should jump at a high height | The player jumps very high | The player jumps too high. When the up key is held for longer than the duration, the player does not come back down | Fixed
| Can the player jump again after landing? | Verify | 3.2.4 | Press the up key after landing | The player should be able to jump | The player jumps | Sometimes, the player can only jump a small height just after landing | Success
| Is the player unable to jump midair? | Verify | 3.2.5 | Press the up key midair | The player should not move up faster | The player jumps again midair | The player can jump in the air many times. Also can hold in the air under a platform. Also carries on moving to the left/right while jumping even after releasing the left/right keys | Fixed
Effect list | Are active effects shown on the HUD? | Verify | 3.3.1 | Pick up an effect item | The item's effect should show up | The effect shows up |  | Success
|  |  | 3.3.2 | Pick up two effect items | Both effects should show up | Both effects show up |  | Success
| Are expired effects removed? | Verify | 3.3.3 | Hit an obstacle and wait for the knockout effect to expire | The effect should disappear | The effect is removed |  | Success
Side borders | Is the player unable to move out of the screen? | Verify | 3.4.1 | Walk to the left of the screen | The player should stop | The player stops |  | Success
|  |  | 3.4.2 | Walk to the right of the screen | The player should stop | The player stops |  | Success
Scrolling screen | Can the screen move in response to the player's movements? | Verify | 3.5.1 | Walk to the right past the middle of the screen | The screen should pan to the right, following the player | The player stops moving in the middle of the screen | The sprites didn't move because their rect positions were not updated | Fixed
|  | Verify | 3.5.2 | Walk to the left | The screen should pan to the left | The screen pans to the left | When jumping next to a platform and moving towards it, the player glitches to the top or the bottom of the platform | Success
|  | Verify | 3.5.3 | Jump up | The screen should move up | The screen moves up |  | Success
|  | Verify | 3.5.4 | Move off a platform | The screen should move down | The course and the player disappears | The screen moves a bit too much out of the course | Fixed
| Will the screen stop scrolling when reaching one of the edges of the course? | Verify | 3.5.5 | Move towards the side of the course | The screen should stop moving horizontally | The screen stops moving |  | Success
|  | Verify | 3.5.6 | Move to the top of the course | The screen should stop moving vertically | The screen stops moving |  | Success
Level clear | Can the level clear region move with the rest of the course? | Verify | 3.6.1 | Have the program draw the EndArea Rect. Move towards the right edge of the course | The Rect should move with the course | The Rect moves to the left |  | Success
| Will the Rect trigger the level clear procedure? | Verify | 3.6.2 | Move into the EndArea Rect | The screen should be replaced with a white background and text saying level clear | Nothing happens |  | Fixed
Level loader | Will the level load as per the level file? | Verify | 3.7.1 | Create a level file. Have the program load from this level file | The level should be built exactly as described by the level file | The level is built as the level file described it |  | Success
| Can the player still move? | Verify | 3.7.2 | Move the player around | The player should move normally | The player moves smoothly on platform, but sometimes slow down when landing | When landing onto a platform and the player moves in between 2 block platforms touching each other, the player horizontally slows down. Sometimes (Very rarely) it falls through the platform | Success
| Can the player still interact with the other sprites? | Verify | 3.7.3 | Move the player into the item/obstacle sprites | The sprites should disappear and apply its effect | The sprites' effects are applied and the sprites disappear | When hitting a platform on the side where a sprites is placed on top of, it can be picked up even if the player does not make it on the platform | Success
Level Transition | Does the game over procedure execute successfully? | Verify | 3.8.1 | Walk into the green EndRect | The level clear text should show over the game and the player should move off the screen | The text shows, but the player freezes in place | playerSprite is not updated | Fixed
| Will the game continue upon user key input? | Verify | 3.8.2 | Press a key during the level clear stage | The level should restart | The game restarts sometimes | The game couldn't check input queue | Fixed
|  |  | 3.8.3 | Make a second level and finish the first level | The second level should load after finishing the first level | The second level loads | When the user accidentally taps another key while hand still at the controls, the game immediately loads the next level. playerSprite is replaced when the new level is loaded | Success
| Will the game end when there are no more levels? |  | 3.8.4 | Finish the second level | The screen should show a white background with "You win" | "You win" shows up |  | Success
Progress Bar | Are both the label and progress bar arranged properly? | Verify | 3.9.1 | Run the game and look at the HUD | The progress bar should be arranged as per the design | The progress bar is too small |  | Fixed
| Does the bar show where the player is in the course? | Verify | 3.9.2 | Move around the level | The red rectangle should move in the same direction as the player | The player moves in the player's direction |  | Success
Enemies | Does the combat system work when colliding into an enemy? | Verify | 4.1.1 | Collide into an enemy | The combat system should appear | The combat bar does not show up and the player quickly dies | The code keeps re-initialising the variables needed in the combat system, The combat bar and key indicator is drawn behind the background. The player stays mid air and partially inside the enemy. | Fixed
| Does the system respond to user inputs correctly? | Verify | 4.1.2 | Collide into an enemy and press the key that is shown above the bar | The black pointer should move forward | The pointer moves forwards |  | Success
|  | Invalid | 4.1.3 | Press any key other than the one shown above the bar | The pointer should not move | The pointer doesn’t move |  | Success
| Does the correct procedures occur for each outcome of the game | Verify | 4.1.4 | Lose the fight against and enemy | The combat should end with the player moving away, as well as losing some health and points | Points and health are deducted, but the combat starts again | Player cannot escape the enemy after losing | Fixed
|  | Verify | 4.1.5 | Win the fight against an enemy | The enemy should disappear and points should be added | Points are added, but the ememy stays put | The enemy is not removed | Fixed
| Does player invincibility work properly? | Verify | 4.1.6 | Lose a fight against an enemy and walk into an obstacle or enemy | The player should flash and pass through the obstacle/enemy unharmed | The player flashes and passes through the obstacle |  | Success
|  | Verify | 4.1.7 | Wait for invincibility to expire and then collide into an obstacle or enemy | The player should stop flashing and interact with the enemy/obstacle | The player interacts with the enemy/obstacle | The player sometimes disappear after its invincibility expires | Success
Tsunami | Does the wave start moving after a certain amount of time? | Verify | 4.2.1 | Wait for the wave for 5 seconds | The wave should start moving | The wave starts moving |  | Success
| Is the wave moving correctly? | Verify | 4.2.2 | Look at where the wave is moving | The wave should move to the right | The wave moves to the right |  | Success
| Will the game end once it collides into the player? | Verify | 4.2.3 | Move into the wave or wait for the wave to catch up | The Game Over screen should show | The Game Over screen appears |  | Success
| Will the wave move back once the next level starts? | Verify | 4.2.4 | Reach the end of the level and start the next level | The next level should load and game should be playable again | The Game Over screen appears after ending the first level | The Tsunami wave is not reset after a new level is loaded | Fixed
Main Menu | Is the Main menu formatted correctly? | Verify | 5.1.1 | Launch the game | The objects on the menu should be arranged as the design | Text on buttons start off as green and each label drawn on top of each other | The button images used the same surface instead of using a copy of the Button surface | Fixed
| Is the user able to interact with the menu? | Verify | 5.1.2 | Move the mouse over the buttons and click one of them | The buttons should change image when hovering the curor and an event should trigger upon clicking. | The button's change image when hovering over the buttons, but nothing happens when clicking on them | Clicking does not trigger buttons. Also, button is triggered at the same time it just gets clicked on | Fixed
|  |  | 5.1.3 | Use the arrow keys to navigate around the menu and press enter on one of the buttons | The menu pointer should move in response to keyboard inputs, and an event should trigger upon tapping enter. | Pointer moves with the inputs and when pressing Start New, the game starts | Menu pointer not synced with mouse pointer. Have to repeatedly tap key. When pressed, cannot be unpressed. When holding enter and pressing arrow keys, previous button stays pressed. | Fixed
| Does each button trigger the correct result? | Verify | 5.1.4 | Trigger the Start Game button | The game should start | The game starts |  | Success
|  |  | 5.1.5 | Trigger the Settings button | The Settings menu should appear | The Settings menu appears |  | Success
|  |  | 5.1.6 | Trigger the other buttons in the Menu | A text object should appear at the bottom saying the feature is unavailable | Text appears |  | Success
Settings Menu | Settings menu arranged correctly? | Verify | 5.2.1 | Select Settings Menu | The Settings menu should appear as described as the design | Most objects are arranged properly, however, there are problems | Drop menus are too long, sliders are too thick, drop menus drawn behind tick box, tick box is completely black | Fixed
| Can keyboard controls traverse the menu? | Verify | 5.2.2 | Draw a graph of the menu's gui map and traverse through each of the edges shown in the graph | The pointer should be able to move across every edges of the graph | Can traverse most paths, but there are problems | Noticeable problems:Can't move between fullscreen tickbox and music slider, 2 up/down key presses to move away from difficulty drop menu, can't move left or right from set jump button
| Do the sliders work normally? | Verify | 5.2.3 | Click on a slider and move the mouse left and right | Slider pointer position should move with the mouse, should not move past the extreme left and right sides of the slider and give the correct output value | Slider pointer follows mouse, but only when clicked on left half of slider. Also, slider values are not between the specified range and pointer cannot be dragged when clicking outside the slider rect | Slider rect size dependent on size of image passed in. Pointer not centered. Can only drag when clicked inside the slide rect | Fixed
|  |  | 5.2.4 | Select a slider with the keyboard and press left and right | Slider pointer position should move one increment per key tap in the same direction as the key pressed, or move repeatedly when key is held. Also should not move past the extreme left and right sides of the slider and give the correct output value | Slider is not being focused | Focused objects are immediately defocused in the next tick | Fixed
| Do the tick boxes work normally? | Verify | 5.2.5 | Click on a tick box | The tick box's appearance and its state should change | The tick box's image changes and its state also changes |  | Success
|  |  | 5.2.6 | Select a tick box with the keyboard |  | When holding enter, the tick box fluctuates between off and on | Nothing stopping tick box to toggle multiple times while holding enter | Fixed
| Can drop menus drop down? | Verify | 5.2.7 | Click on a drop menu | The options list should drop down, along with a scroll bar | The drop list drops down with a scrollbar |  | Success
|  |  | 5.2.8 | Select a drop menu with the keyboard |  | Drop menu drops list, but a bug when holding enter | List disappears with the last option in the dropped list selected. Takes 2 enter presses to undrop again | Fixed
| Can the user traverse through the options in a drop menu? | Verify | 5.2.9 | Move the mouse over the options, and drag the scrollbar | The option under the cursor should highlight. New options should show when dragging the scrollbar | Only the last option in the list highlights. Scrollbar cannot be interacted with | The drop list interferes with the scrollbar. Also, scrollbar is too short | Fixed
|  |  | 5.2.10 | Press up and down after selecting a drop menu | The pointer should move up and down, when reaching the top or bottom of the list, it should scroll up or down | Pointer moves with inputs, drop list scrolls correctly | When list drops again, the pointer always returns back to the first line in the list | Success
| Can the user select an option from the drop down list? | Verify | 5.2.11 | Click on an option in the option list | The drop down list should disappear with the selected option | The clicked option is selected as the list disappears | Mouse activates slider under the drop list when the list pulls up | Success
|  |  | 5.2.12 | Select an option in the list with the keyboard |  | Pointed option is selected |  | Success
| Can the drop menus undrop its options list? | Verify | 5.2.13 | Click on the drop menu box or anywhere else in the screen but the drop down list | The drop down list should disappear | When clicking outside the drop menu, the list pulls up, but nothing happens when clicking on the top box | Box rect does not respond to clicks | Fixed
| Will the mouse and keyboard not interfere with each other? | Verify | 5.2.14 | Move the mouse first and then press the arrow keys | Menu should only respond to mouse movement | Pointer appears while mouse is moving, but not significant. No other significant interferences |  | Success
|  |  | 5.2.15 | Press arrow keys first and then move the mouse | Menu should only respond to keyboard inputs | There are interferences with buttons and sliders | When focusing on sliders, once the mouse moves, the game crashes with "Slider object has no attribute 'get_dropped'". When holding a button with the keyboard, when moving the mouse, the button triggers. Also, when focusing on a slider, mouse cannot select anything else | Fixed
Score by distance | Will points be added when player moves forward | Verify | 6.1.1 | Move the player forward | The score should increase by 10 each time | The score increases by 10 each time |  | Success
| What happens when the player moves back and forward again? | Invalid | 6.1.2 | Move the player back by a large distance and then move forward | No points should be added to score | The score does not increase |  | Success
|  | Verify | 6.1.3 | Move the player back from a landmark and then move past that landmark | The points should increase again by 10 each time | Score increases by 10 |  | Success
| Is points added per tile? | Experimental | 6.1.4 | Have each platform draw a border. Move a certain number of tiles | The points added should be 10 times the tile distanced moved | After moving 10 tiles, the score is 100 |  | Success
Menu Navigation | Will the validate map method pick up invalid entries? | Invalid | 6.2.1 | Change one of the nodes to a non-string | The console should print out a warning | The console shows that the program noticed the error | The validate method could not concatenate an integer | Success
|  |  | 6.2.2 | Change one of the nodes to more than one character |  | The console shows that the program noticed the error |  | Success
|  |  | 6.2.3 | Change one of the field values to a non string |  | The console shows that the program noticed the error |  | Success
|  |  | 6.2.4 | Change one of the field values to an empty string |  | The console shows that the program noticed the error |  | Success
|  |  | 6.2.5 | Change one of the directional field values to more than one character |  | The console shows that the program noticed the error |  | Success
|  |  | 6.2.6 | Change one of the directional field values to a value that is not one of the nodes |  | The console shows that the program noticed the error |  | Success
|  |  | 6.2.7 | Change one of the "obj name" values to a value that is not a name of one of the menu's objects |  | The console shows that the program noticed the error |  | Success
| Will the pointer navigate around the menu properly? | Verify | 6.2.8 | Following the map graph, traverse through all the edges in the graph | The pointer should be able to traverse through all the edges | The pointer traverses through all the edges |  | Success
Settings | Will the screen and visual objects adjust properly after resolution changes? | Verify | 6.3.1 | Change the resolution, scale and position factor variables | Menu objects and HUD objects should be adjusted correctly | Many problems | Buttons shrink when hovering cursor over, slider pointer not aligned | Fixed
| Will the settings menu apply the correct resolution changes? | Verify | 6.3.2 | Go to the settings menu, select another resolution and apply the settings | The screen and objects (apart from game entities) should be adjusted to the new resolution | Screen changes, but objects stay the same size and position | Objects do not resize and reposition | Fixed
| Will the settings menu set fullscreen mode appropriately? | Verify | 6.3.3 | On the settings screen, toggle the fullscreen tick box and click apply | Screen should toggle fullscreen | The game goes to windowed mode |  | Success
| Will the apply button set changes to settings? | Verify | 6.3.4 | Change the resolution and click apply | The screen should change to the new resolution | The screen changes to new resolution |  | Success
| Will default button reset the settings? | Verify | 6.3.5 | Change the settings and then click the default button | The settings menu should reset and the default settings should be applied | Nothing happens | Default settings share same dict object with settings dict, settings menu does not reset | Fixed
| Will the settings menu go back to what it was before when leaving without applying? | Verify | 6.3.6 | Change some options in the settings menu and click back. Then go back to the settings menu | The settings menu should go back to what it was before being changed | Settings stayed as it was after the change | Back button does not set back settings | Fixed
| Does the key binding procedure perform correctly? | Verify | 6.3.7 | Bind key "A" to left | The A key should be set to left | Key A is set |  | Success
|  | Verify | 6.3.8 | Bind key "D" to right | The D key should be set to right | Key D is set |  | Success
|  | Verify | 6.3.9 | Bind space key to jump | The space key should be set to jump | Space key is set |  | Success
|  | Verify | 6.3.10 | Wait for 5 seconds | Counter should run out and control reset to previous setting | Key binding reset to space |  | Success
|  | Verify | 6.3.11 | Try the game with new controls | The game should respond to the new controls correctly | A and D works, but space does not | New key bindings not set between game files | Fixed
Upgrade shop | Is the menu formatted properly? | Verify | 6.4.1 | Complete the level and press any key to continue to the shop menu | The menu should be formatted as shown in the UI design | Mostly formatted correctly, apart from the price labels | Price labels come out of the panel, in smaller resolutions, the white bar is too thick and too close to the pointer | Fixed
| When upgrading, is money correctly deducted and the price increased? | Verify | 6.4.2 | In the shop menu, click on one of the right arrow buttons. | The bar next to the button should increase by one, the price of the trait taken from money left and the price should increase | Health level meter increases by 1, 30 gold taken away and price increases to 40 |  | Success
| When downgrading, is money correctly refunded and price decreased? | Verify | 6.4.3 | In the shop menu, click on one of the left arrow buttons. | The bar next to the button should decrease by one, the previous price of the trait added to money left and the price should decrease | Health level meter decreases by 1, 30 gold added to money left and price drops to 30 |  | Success
| Is upgrading and downgrading limited between initial level and max level of 8? | Extreme | 6.4.4 | Try to upgrade past level 8 | The bar should not continue to increase past level 8 and the money and price values should not change | Health level meter does not increase, money left and price stay the same | Shop still show price even though you can't upgrade when maxed out | Success
|  | Extreme | 6.4.5 | Try to downgrade below level 0 | The bar should not continue to decrease past level 0 and the money and price values should not change | Health level meter does not decrease, price and money left stay the same |  | Success
|  | Extreme | 6.4.6 | Add another level, upgrade some traits in the shop after the first level. When reaching the shop after the second menu, try downgrading one of the previously upgraded traits | The selected trait should not downgrade | The traits do not downgrade |  | Success
| Can the levels be reset to their initial values? | Verify | 6.4.7 | In the shop, upgrade some traits but then click reset afterwards | The upgraded traits should go back to level 0 and the spent money refunded | The traits go back to level 0 |  | Success
|  | Verify | 6.4.8 | Upgrade traits after the first level, continue to the second level, upgrade some traits in the shop after that level and then press reset | The upgraded traits should go back to their initial levels and the spent money refunded | All the traits go back to their levels before the change |  | Success
| Are the upgrades actually applied? | Verify | 6.4.9 | Max upgrade health and press continue | Max health should be increased in the next level | Max health increased to 18 | Exceeds max allowed health of 10 | Fixed
|  | Verify | 6.4.10 | Max upgrade speed and press continue | The player should be able to go faster | Player's max speed increased and completes the course in 2 seconds | Max speed upgrade increases speed too much
|  | Verify | 6.4.11 | Max upgrade acceleration and press continue | The player should accelerate faster | Player accelerates faster |  | Success
|  | Verify | 6.4.12 | Collide into an enemy and attack. Then, max upgrade strength, press continue, collide into an enemy and attack | The player should be able to deal more damage in the 2nd level than the 1st | The player one-hit kills the enemy | Strength upgrade increase too much
|  | Verify | 6.4.13 | Collide into an enemy and watch its attacks. Then, max upgrade defence and press continue, collide into an enemy and wait for the enemy attack | The enemy should not deal as much damage than in the 1st level when in the 2nd level | Enemy damage reduced to one third |  | Success
Feature | Test for | Issue | Test ref | Description | Fixes/potential fixes
Settings Menu | Check for robustness | Invalid | 7.1.1 | The game crashes when an unsupported resolution mode is applied | The game now removes unsupported resolution modes from the list
|  | Bug | 7.1.2 | Changing the resolution frequently causes image quality to deteriorate, due to frequent resizing | Only resize the screen Surface after everything is drawn onto it before updating it onto the screen
Game mode | Check for robustness | Bug | 7.1.3 | Physics is dependent on clock time, rather than real time. This can be an issue when the game lags, as this affects the movement | None
|  | Invalid | 7.1.4 | Whenever a new level is loaded, warning messages fill the console concerning an object name change | After a level is completed, remove the objects in the level from the object names list
|  | Bug | 7.1.5 | The Tsunami wave is only the same height as the resolution height. This can be an issue with courses that are taller than the screen | The Tsunami is now instanced with the length and height of the course
|  | Design flaw | 7.1.6 | Level files use space for an empty tile. This is an issue with level design, as the course dimensions is not immediately seen | Create a level builer, so it has usable GUI that makes it easier for level building.
Windows Executable | Check for robustness | Invalid | 7.1.7 | When running the compiled executable on Windows XP, the program crashes with a missing .dll file. Then, it also crashes as it can't find SetProcessDpiAware. | Download and put the missing .dll file into the .zip file. Also, only set dpi aware when the operating system is Vista or higher
|  | Invalid | 7.1.8 | The compiled game is not supported by 32 bit systems | Compile game in 32-bit Python and Pygame
Upgrades | Check for usability | Bug | 7.2.1 | Speed and Strength upgrades seem to increase their traits too much | Change the ratio of how the speed and strength increases per upgrade
|  | Design flaw | 7.2.2 | The upgrades may not be easily affordable in the first few levels | Either make the costs of upgrades cheaper, or put more money items in the levels
Learning the game | Check for usability | Missing feature | 7.2.3 | There is no How to Play screen, which is important to show controls and the different objects | Add a screen that describes each item and obstacle and their effects, as well as controls and aim of the game
Playing the game | Check for usability | Design flaw | 7.2.4 | The player can just easily run through the course on the ground, as there is little obstacles there | Break up the ground, and make the player die when falling through a gap. Or put walls to force the player to move up. Or make some platforms deal damage when landing on it
|  | Bug | 7.2.5 | The enemy combat is too random and unpredictable. Sometimes the enemy starts not doing anything for a while, other times it would quickly kill you | None
|  | Missing feature | 7.2.6 | There is no way to pause the game, which can be inconvenient for the player | Create a pause subroutine, where the game is suspended to run this pause subroutine.